## Projecttijdlijn
projecttijdlijn van vier weken
Begindatum: | 2024-02-12
Toegewezen aan: | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 7 | [6 empty] | Week 7 | [6 empty] | Week 7 | [6 empty] | Week 7 | [6 empty] | Week 7 | [6 empty] | Week 7 | [6 empty] | Week 7 | [6 empty] | Week 7 | [6 empty] | Status:
| feb | [6 empty] | feb | [6 empty] | feb | [6 empty] | mrt | [6 empty] | mrt | [6 empty] | mrt | [6 empty] | mrt | [6 empty] | apr | [6 empty] | apr | [6 empty] | apr | [6 empty] | apr | [6 empty] | apr | [6 empty] | mei | [6 empty] | mei | [6 empty] | mei
| ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo
 | time axis 2024-02-12 to 2024-05-26
1. Brainstorm | [105 empty] | wordt uitgevoerd | bar: 2024-02-12 to 2024-02-29
1.1 AI model zoeken | 2024-02-15: Samen | voltooid
1.2 Batterij zoeken | 2024-02-22: Samen | voltooid
1.3 Trilmotoren zoeken | 2024-02-22: Samen | wordt uitgevoerd
2. Software implementatie | [105 empty] | wordt uitgevoerd | bar: 2024-02-22 to 2024-04-18
2.1 AI pipelinen | 2024-02-22: Xander | wordt uitgevoerd
2.2 Verwerking data | 2024-02-22: Thijs | wordt uitgevoerd
2.3 Herkenning van situaties | 2024-03-14: Thijs | niet gestart
2.4 Onverwachte bugs bij samenvoeging | [105 empty] | niet gestart | bar: 2024-03-29 to 2024-04-18
3. Hardware implementatie | [105 empty] | niet gestart | bar: 2024-03-14 to 2024-04-25
3.1 Electronica | 2024-03-14: Xander | niet gestart
3.2 Mechanisch | 2024-03-14: Xander | niet gestart
4. Testing | [105 empty] | niet gestart | bar: 2024-02-29 to 2024-05-26
4.1 Software | 2024-02-29: Samen | niet gestart
4.2 Hardware | 2024-04-19: Samen | niet gestart
5. Deadlines proffesionele competenties | bar: 2024-03-06; 2024-03-08; 2024-04-11; 2024-04-24; 2024-05-08; 2024-05-21